## Sheet1
Monster-UI Test Plan
Application Name |  | Appstore (and apploader)
Version |  | 1
Purpose of the application |  | The Appstore was created to allow an admin to choose which apps should be available to their users. The Apploader is a mean to navigate between the available apps.
Prerequisites |  | For this test plan, you will need: - A newly created account, with at least two user (one admin and one regular user) for which you know the login credentials. They will be refered to as [admin] and [user]. - At least 4 apps available, that will be called [App1-4] (you can use, for example: Accounts Manager, Number Manager, SmartPBX, PBX Connector)
Roles |  | Standard Account
Specificities |  | If a different user(admin) makes changes on the appstore, the changes will only take effect for you at your next connection
| ID | Description
| 1 | Enabling some Apps
| Steps | Actions | Expected | Pass / Fail |  |  |  | Comment
|  |  |  | User | Masquerading | Reseller | Superduper
| A | Log in your brand new account using the admin's creds | The appstore is automatically loaded, listing all the Apps, none of them being currently enabled |  |  | N/A | N/A
| B | Click on the "APPS" button on the left of the black top bar. | An empty sidebar opens (since you have no apps enabled yet), with only an "Appstore" button at the bottom. |  |  | N/A | N/A
| C | Click on the "APPS" button again | The sidebars gets closed |  |  | N/A | N/A
| D | Click on the [App1] box | A popup opens, giving you a preview of the app if available, a description and some other details, as well as an On/Off toggle buton |  |  | N/A | N/A
| E | Toggle the app on | After a short processing time, the App is enabled, briefly showing a green ✓ next to the toggle button. The section who can use this app is now displayed, with "All users" selected by default. |  |  | N/A | N/A
| F | Close the popup by clicking on the top-right cross, or pressing ESC | The popup closes, and the [App1] box now has a green ✓ displayed in the top-right corner. |  |  | N/A | N/A
| G | Repeat steps D-E for [App2], then select the "Admins only" radio button. | After a short processing time, the setting is updated, briefly showing a green ✓ next to the toggle button. |  |  | N/A | N/A
| H | Close the popup by clicking on the top-right cross, or pressing ESC | The popup closes, and the [App1] box now has a green ✓ displayed in the top-right corner. |  |  | N/A | N/A
| I | Repeat steps D-E for [App2], then select the "Specific users" radio button. | A link appears below, indicating that no user has been selected yet |  |  | N/A | N/A
| J | Click on that link | The whole box changes into a user selection box, indication the number of users selected (0/total) |  |  | N/A | N/A
| K | Click on select all link | All the check box are checked, and the selected number on top is updated |  |  | N/A | N/A
| L | Click on unselect all link | All the check box are unchecked, and the selected number on top is updated |  |  | N/A | N/A
| M | Type [user]'s first name in the search box | The list of user is filtered, showing only names matching the one you typed |  |  | N/A | N/A
| N | Click on [user]'s row | The [user]'s checkbox is checked, and the selected number on top is updated |  |  | N/A | N/A
| O | Click on Save | The user selection box changes back to its original state, and the "no selected user" link now displays the number of selected users (i.e. "Selected Users (1)"). In addition, after a short processing time, the setting is updated, briefly showing a green ✓ next to the toggle button. |  |  | N/A | N/A
| P | Close the popup by clicking on the top-right cross, or pressing ESC | The popup closes, and the [App1] box now has a green ✓ displayed in the top-right corner. |  |  | N/A | N/A
| Q | Open the Apploader (APPS button on top bar) | [App1] and [App2] are both listed in the apploader. [App3] is not, as you enabled it only for [admin], nor is [App4] as it is not enabled. |  |  | N/A | N/A
| R | On a separate browser (or using the incognito mode of your current browser), log in Monster UI using [user]'s credentials | You landed on either [App1] or [App3] (whichever is first in alphabetical order). In addition, the Appstore button at the bottom is not available. |  |  | N/A | N/A
| S | Open the Apploader (APPS button on top bar) | [App1] and [App3] are both listed |  |  | N/A | N/A
| ID | Description
| 2 | Filtering and Searching
| Steps | Actions | Expected | Pass / Fail |  |  |  | Comment
|  |  |  | User | Masquerading | Reseller | Superduper
| A | Open the Apploader (APPS button on top bar), and click on the Appstore button (bottom) | The appstore is loaded, displaying all available apps by default |  |  | N/A | N/A
| B | In the search field (top-right), type in [App1]'s name | The listing of apps gets filtered as you type, only showing the apps with a name matching your search |  |  | N/A | N/A
| C | On the left side, click on "My Apps" | Only the enabled apps are now listed (and the search field has been reset) |  |  | N/A | N/A
| D | On the left side, click on "Resellers Apps" | Only the apps tagged as reseller apps are now listed |  |  | N/A | N/A
| E | On the left side, click on "Carriers Apps" | Only the apps tagged as carrier apps are now listed |  |  | N/A | N/A
| F | On the left side, click on "Developers Apps" | Only the apps tagged as developer apps are now listed |  |  | N/A | N/A
| G | On the left side, click on "All Apps" | All the available apps are listed again |  |  | N/A | N/A
| ID | Description
| 3 | Disabling an App
| Steps | Actions | Expected | Pass / Fail |  |  |  | Comment
|  |  |  | User | Masquerading | Reseller | Superduper
| A | In the Appstore, click on an enabled app you want to disable | The app popup opens up |  |  | N/A | N/A
| B | Toggle off the toggle button | After a short processing time the app gets disabled, briefly showing a green ✓ next to the toggle button. |  |  | N/A | N/A
| C | Close the popup by clicking on the top-right cross, or pressing ESC | The popup closes, and the app's box doesn't have a green ✓ in the top-right corner anymore. |  |  | N/A | N/A
| D | Open the Apploader (APPS button on top bar) | The app you just disabled is not listed there anymore |  |  | N/A | N/A
| ID | Description
| 4 | Setting the default app
| Steps | Actions | Expected | Pass / Fail |  |  |  | Comment
|  |  |  | User | Masquerading | Reseller | Superduper
| A | In the Appstore, enable at least two apps, then open the apploader | Your enabled apps are listed, and the top one has a "default" green dot. The one currently on the top will be refered to as [A] and the one right below as [B] |  |  | N/A | N/A
| B | Using the part on the LEFT of the [B]'s icon, drag&drop it to put it at the top of the list | [B] is now your default app |  |  | N/A | N/A
| C | Click on [A] | The app [A] is loaded |  |  | N/A | N/A
| D | Open the apploader | [A]'s name is now displayed in blue, indicating it's the app currently used |  |  | N/A | N/A
| E | Refresh the page on your browser | The app [B] is loaded |  |  | N/A | N/A
| F | Open the apploader | [B]'s name is now displayed in blue, indicating it's the app currently used |  |  | N/A | N/A

## Sheet2
A | B | Pass
C | D | Fail
E | F
G | H
I | J
K | L
M | N
O | P
Q | R
S | T
U | V
W | X
Y | Z